## Read me
MVP Scoping & Estimation Sheet
Saurav Kumar Nanda · https://sauravnanda.com/
HOW TO USE
• Use at kickoff. One row per feature. Fill effort in engineer-days (best-case).
• MoSCoW column forces honesty: Must ships v1, Should ships v1.1, Could is parking lot.
• Cut First? = your explicit pre-commitment of what to drop if the timeline slips.
• Summary cells auto-total effort by MoSCoW tier so you can see if scope is realistic.
• If Must-have effort > 70% of your runway, you're scoped wrong. Cut.
© 2026 Saurav Kumar Nanda — free for personal & commercial use. Attribution appreciated.
Questions? hello@sauravnanda.com

## Scope
Feature | MoSCoW | User story | Effort (days) | Risk (L/M/H) | Dependency | Cut First? | Sprint
Signup + email verify | Must | As a user I can create an account via email | 3 | L | SendGrid | No | 1
Google OAuth | Must | As a user I can sign in with Google | 2 | L | Google API | No | 1
Onboarding flow | Must | New user reaches first value in 3 steps | 5 | M | Product copy | No | 1
Dashboard v1 | Must | User sees 3 core metrics on landing | 6 | M | Data pipeline | No | 2
Data import (CSV) | Must | User uploads CSV and sees ingested data | 4 | M | File storage | No | 2
Empty states | Must | Every screen has a helpful empty state | 2 | L | Design | No | 2
Email notifications | Should | User gets weekly digest | 3 | L | SendGrid | Yes | 3
Admin panel | Should | Internal team can view all users | 4 | L | Auth | Yes | 3
Saved views | Should | User saves filtered dashboard views | 3 | M | None | Yes | 3
Search | Should | User searches across records | 5 | M | Indexing | Yes | 4
Billing (Stripe) | Should | User upgrades to paid plan | 6 | M | Stripe API | No | 4
CSV export | Should | User exports filtered data | 2 | L | None | Yes | 4
Public API | Could | Programmatic access via REST API | 12 | H | Rate limiting | Yes | 5
Slack integration | Could | Notifications post to Slack | 6 | M | Slack API | Yes | 5
Mobile app (iOS) | Could | Read-only iOS companion app | 40 | H | React Native | Yes | Post-MVP
Realtime collab | Could | Multiple users edit simultaneously | 20 | H | WebSockets | Yes | Post-MVP
Dark mode | Could | Theme toggle with system default | 2 | L | Design tokens | Yes | 6
Audit log | Could | Admin sees who did what | 4 | M | Eventing | Yes | 6
TOTAL BY TIER
Must
Should
Could
GRAND TOTAL EFFORT