## Read me
Product Roadmap & RICE Prioritization
Saurav Kumar Nanda · https://sauravnanda.com/
HOW TO USE
• This sheet helps you score product bets using the RICE method (Reach × Impact × Confidence ÷ Effort).
• Fill the Roadmap tab. Columns Reach, Impact, Confidence, Effort drive the RICE score automatically.
• Strategic Fit (1-5) is qualitative — how well the feature ladders to your north-star theme.
• Sort by RICE Score descending to pick the next quarter's top 5-8 features.
• Conditional color-coding: green = top third, red = bottom third. Review weekly.
© 2026 Saurav Kumar Nanda — free for personal & commercial use. Attribution appreciated.
Questions? hello@sauravnanda.com

## Roadmap
Feature | Theme | Quarter | Reach (1-10) | Impact (1-10) | Confidence (%) | Effort (days) | RICE Score | Strategic Fit (1-5) | Owner | Status | Notes
Onboarding checklist v2 | Activation | Q2 2026 | 8 | 9 | 8000% | 12 |  | 5 | PM | In progress | Tied to activation rate north-star
Self-serve signup flow | Acquisition | Q2 2026 | 9 | 8 | 7500% | 18 |  | 5 | PM+Eng | Planned | Unblocks PLG motion
Weekly digest email | Retention | Q2 2026 | 7 | 6 | 9000% | 4 |  | 4 | Growth | Ready | Low effort, high lift
Annual billing toggle | Monetization | Q2 2026 | 5 | 7 | 8500% | 8 |  | 4 | Ops | Planned | +15% expected ARPU
Referral program v1 | Acquisition | Q3 2026 | 6 | 7 | 6000% | 20 |  | 3 | Growth | Exploring | Needs design partner test
Mobile app v1 | Retention | Q4 2026 | 8 | 9 | 5000% | 60 |  | 5 | Eng | Backlog | High effort, big bet
Usage-based pricing | Monetization | Q3 2026 | 6 | 8 | 5500% | 25 |  | 4 | Finance | Research | Pilot with 3 accounts first
In-app video tutorials | Activation | Q2 2026 | 6 | 5 | 8000% | 6 |  | 3 | PM | Ready | Cuts time-to-value
Saved search filters | Retention | Q3 2026 | 5 | 6 | 8500% | 5 |  | 3 | Eng | Ready | Top customer request
Slack integration | Activation | Q3 2026 | 7 | 7 | 7000% | 15 |  | 4 | Eng | Planned | Top 3 asked integration
Admin dashboard v2 | Retention | Q4 2026 | 5 | 6 | 8000% | 14 |  | 3 | PM | Backlog | Enterprise unlock
SSO/SAML | Monetization | Q3 2026 | 4 | 8 | 9000% | 20 |  | 4 | Eng | Planned | Unblocks $50k+ deals
Realtime collaboration | Retention | Q4 2026 | 7 | 8 | 4500% | 45 |  | 4 | Eng | Research | Big lift, unknown demand
Custom reporting | Retention | Q3 2026 | 6 | 7 | 7000% | 16 |  | 4 | PM | Planned | Replaces CSV export hack
Free tier limits UI | Activation | Q2 2026 | 6 | 5 | 9000% | 3 |  | 3 | Design | Ready | Nudge to paid conversion
Public changelog | Activation | Q2 2026 | 4 | 3 | 9500% | 2 |  | 2 | Marketing | Ready | Quick win for trust
AI auto-suggest | Acquisition | Q4 2026 | 8 | 7 | 4000% | 50 |  | 3 | Eng | Exploring | LLM moat play
Email deliverability fix | Activation | Q2 2026 | 7 | 6 | 9500% | 5 |  | 4 | Ops | In progress | Current 14% bounce rate
API v2 (public) | Monetization | Q4 2026 | 5 | 7 | 7500% | 22 |  | 4 | Eng | Planned | Developer acquisition channel
Churn-risk alert | Retention | Q3 2026 | 6 | 8 | 6500% | 12 |  | 5 | Data | Research | Needs ML pipeline