## Read me
Weekly Product Operating Cadence
Saurav Kumar Nanda · https://sauravnanda.com/
HOW TO USE
• Fill one row per week on Monday mornings. 15-20 minutes per row, no exceptions.
• Shipped = what ACTUALLY went live, not what was worked on.
• Metric delta = your one north-star number's week-over-week change (%).
• Review quarterly: look at 12 rows side-by-side for patterns in risk → shipped → delta.
• This is not a status report. It's a forcing function for honesty.
© 2026 Saurav Kumar Nanda — free for personal & commercial use. Attribution appreciated.
Questions? hello@sauravnanda.com

## Monday Review
Week of | Shipped last week | Committed this week | Top risk | Metric Δ (%) | Notes
2026-01-05 | Onboarding v2 launched | Referral program build | Email deliverability |  | W1 baseline
2026-01-12 | Email deliverability fix | Dashboard v1 code complete | API rate limit | 240% | Good lift from onboarding
2026-01-19 | Dashboard v1 | Billing (Stripe) spike | Stripe KYC delay | 180%
2026-01-26 | Stripe integration | Saved views | Churn uptick | -60% | Red flag — investigate
2026-02-02 | Saved views | Email digest | Unclear — investigating churn | -120% | Customer research week
2026-02-09 | Email digest | Pricing test | Small sample for test | 30%
2026-02-16 | Pricing test live | Referral program launch | Referrals underbuilt | 90%
2026-02-23 | Referral program v1 | SSO/SAML spec | Enterprise deal stalled | 150%
2026-03-02 | Slack integration | SSO/SAML build | Eng capacity | 210%
2026-03-09 | SSO/SAML | Customer interviews x20 | None | 170%
2026-03-16 | Customer interviews | Churn-risk alert | Data pipeline gaps | 240% | Pattern: data infra debt
2026-03-23 | Churn-risk alert v1 | Onboarding v3 plan | Scope pressure | 320% | Best week QTD

## Rituals
THE 30-MINUTE MONDAY REVIEW
0:00 — 0:05 | Read north-star metric aloud. No commentary yet.
0:05 — 0:12 | Go around: what shipped last week? (facts only)
0:12 — 0:20 | Commit this week: one sentence per person. No maybes.
0:20 — 0:25 | Top risk: one thing that could blow up this week.
0:25 — 0:30 | Write notes. Close laptop. Ship.